## Sheet1
Milestone List | Details
Develop Project Logo | Have a develop product logo that can be printed onto product
Fit product into 3D Printed Case | Design and print a case once hardware is completed.
Have a working hardware product | PCB board is complete with all added modules.
Working software product | Usable software with developed back-end
Connect Hardware and Software | Integrate hardware and software, final milestone
Develop Proper easy UI | Have a proper consumer facing UI that's easy to understand and use.
Member Assigned | Task/Milestone | Start | Completion | #hours
Nihaal | Organize Student Meetings | 2025-10-06 | 2025-10-25 | 10
Nihaal | Maintain Design Notebook | 2025-10-10 | 2026-04-26 | 25
Nihaal | Design Logo | 2025-10-15 | 2026-02-13 | 10
Nihaal | Determine Development Languagues | 2025-10-11 | 2025-10-28 | 12
Nihaal | Manage Team Budget | 2025-10-02 | 2026-11-15 | 15
Nihaal | Research Develoment Environemnt | 2025-09-20 | 2025-10-30 | 5
Keegan | Combine components to build prototype | 2025-12-20 | 2026-02-04 | 30
Keegan | Research PCB's and categorize | 2025-10-06 | 2026-11-05 | 11
Keegan | Research GPS Modules and categorize | 2025-10-06 | 2026-11-06 | 11
Keegan | Decide on Hardware Style Choices | 2025-10-09 | 2026-11-07 | 11
Keegan | Design 3D Case Module | 2025-10-09 | 2025-11-04 | 25
Keegan | Find and Utilize 3d printer | 2025-10-01 | 2025-11-05 | 5
Corey | Decide on style choices to match hardware | 2025-11-11 | 2025-11-21 | 8
Corey | Research Tracker software | 2025-09-12 | 2025-11-12 | 5
Corey | Research GPS module firmware | 2025-10-06 | 2025-11-08 | 5
Corey | Determine Back end language and implementation | 2025-10-10 | 2025-11-28 | 4
Corey | Determine Front-End language and Implementation | 2025-10-10 | 2025-11-28 | 4
Nihaal | Develop Project Logo | 2025-12-01 | 2026-02-13 | 10
Keegan | Fit Product into 3D printed Case | 2026-01-17 | 2026-03-16 | 1
Keegan | Have a working Hardware product | 2025-11-20 | 2026-02-16 | 25
Corey | Working Software product | 2025-11-19 | 2026-02-16 | 20
Corey/Nihaal | Connect Hardware and Software | 2026-02-24 | 2026-03-05 | 17
Corey | Develop Proper easy UI | 2025-10-21 | 2026-02-28 | 18